## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/10-05/14 | Team structure: Collaboratively assigned team roles, established weekly meetings and communication expectations. Planning: Team lead documented requirements with assistance from other team members, each member contributed to filling out SPPP and risk management form, Technical setup: Team lead set up pivotal tracker, configuration lead created github repo and team members joined and added their bios. Team lead reviewed changes and config lead merged into main branch, Presentation: Brooke took the lead on distilling iteration 0 work into presentation slideshow and video | Not all members familiar with Pivotal Tracker and had to get up to speed on how it works. Technical progress is waiting on product requirement clarity before implementation. Not all team members have React experience so this is expected to add some challenges as we move forward. | Requirements were difficult to determine as we are reliant on the other team's decisions to determine what they need. | Preliminary requirements were documented but continuing to communicate across teams to refine their accuracy to all teams' needs. | 18 | 2 |  |  |  | 43.5 | Brenna - 16 Brooke - 6 Natanim - 8 Lillian - 9.5 Fehmi - 6 | 2.5
1 | 05/15-05/29 | Solidifying requirements: Meeting with all teams and professor allowed us to get a clearer idea of our requirements and which teams we'll be working with for our backend. We made the decision not to support team 3's learning platform to narrow our scope. Cross team collaboration: Team lead communicated with other teams and reviewed their documents to understand their services and make sure our UI will align with them on pieces like login type, and project fields. Project structure: Brooke, our design and Implementation lead created a skeleton React project to get us started and determined a file organization strategy in collaboration with our team. Beginning development: Brooke began development, creating a 404 error page and building out our navigation, and beginning to build our dashboard UI. All other team members have also been assigned tickets and are focusing on building out UI for our most important features this iteration. Integration with backend will be a focus next iteration when other teams have had more time to setup their services. Configuration lead has been merging PRs whenever they are ready. | There were some difficulties getting everyone's local projects in sync and there was some confusion around pull requests. We worked on getting our project files organized the same and only pushing the necessary files to reduce merge conflicts and getting team familiar with the PR process. | Requirements changed at the beginning of this iteration which meant we needed to rework some of our plans. The exact details of how we will integrate our UI with other teams' services is still to be determined and remains a challenge for us. Additionally, two team members had to take trips out of town, impairing development tool access and slowing progress. | Requirements have now been determine so solid progress was made there. Will need to continue cross team communication for integration moving forward. | 18 | 4 |  |  |  | 47 | Brenna - 17 Brooke - 3 Natanim - 12.5 Lillian - 8 Fehmi - 7 | 2 | 9.5 | 1 | 6 | 8 | 2.5 | 3.6 | 1.5
2 | 5/30-6/11 | Design completion: Brooke created a fleshed out UI design with Canva, building off of the wireframes from the previous iteration. UI style updates: Lillian added in the colors and fonts and Brooke added the icons to the project. The team then updated their features to use the theme and have the UI styling match the design. Beginning integration with services: Brenna communicated with and had meetings with other teams to get info on services and how to begin integrated them with our UI. Nati began writing the code to use their API and auth services. Testing: Fehmi filled out our software testing document. Brooke added Jest into the project and the team began writing unit tests for their features. Software design: Our software design document needed some reworking after the last iteration to refine our architecture and software design plan | Integration with other team's services is a challenge for us. Team 2's api they told us is ready for us to use as of 6/6 but is not yet deployed so in order to make calls to it we would have to run their code locally on all our machines. We requested instuctions for how to run their code but have no received a document or readme detailing this yet. Nati succeeded at running their code but found some issues causing some calls to not work so we're waiting on fixes from them still. Team 1 faced some challenges that caused some delays so we only got access to their service two days ago. | Communcation has had some delays both within our team and between our team and the other teams. It is difficult to schedule meetings with everyone's busy schedules and vastly different time zones across the world, and asynchronous commications can be slow and messages sometimes missed by team members leaving them out of the loop. | Need to continue communicate with other teams to work out remaining challenges for integration. The short timeline for the final iteration will require strong communication and coordination within our team to divide and complete remaining work. | [6 empty] | Brenna - 16.5 Brooke - 8.2 Natanim - 7.5 Lillian - 15 Fehmi - 13 | 2 | 5 | 0.5 | 4 | 22.5 | 7.5 | 5.1 | 1.5
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Brenna Mahn |  |  | Design Patterns section, Class Diagram, Architecture Section (Brooke did most, I added some writing and the diagram) |  | Made Iter 1 slide and presentation with Fehmi | Made project creation form | Wrote unit test for project creation form feature |  | Communicated with team via discord and meetings to check in on progress and make assignments. Acted as a liason between my team and other teams whose services we are using.
Savien Brooke Love |  |  | Made the summary for the Software Architecture and UI design. As well as contributed to the Design Patterns |  | Created the Iteration 0 and Presentation. Created the Demo for Iteration 01 | Created the initial setup for React. Created the routes for all of the pages. Coded the Dashboard, Project card, and Project Modal |  |  |  | Did most of the Meeting Minutes for the week. Created the Figma and Canva wireframes. Created some Zoom Meetings.
Fehmi Baltaci
Natanim Eibrahim
Pinwen Mu

## Natanim Eibrahim
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/14 | 8 | 5.5 | 2.5 | 0 - learn pivotal tracker and watch tutorials 1 - define non-functonal requirements 5 - participate in team meetings 6 - revise and setup git 7 - work on the project overview 7 - research similar projects and similar products and work on the related work of the the SPPP document 7 - define the mangement plan of the SPPP document 7 - work on the Integration and deployment risk management details 7 - work on lab1 and collaborate with team | 1.5 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1. Participated in 4 section of the SPPP document 2. Write 1 section (Integration and Deployment) if the Risk Management 3. Setup git and collaborate on lab1 team.md update my information and created a commit message | 1. not familar with pivotal tracker 2. |  | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2024-02-03 | 05/15-05/29 | 8.5 | 7.5 | 1 | 0 - revising react and pivotal tracker 3 - Registration and Login Form 5 - Participate in team meetings 7 - work on lab 2 7 - create user story tickets on pivotal tracker | 3 | 0 | 1.5 | 1 | 0.5 | 0.5 | 0 | 1
2024-03-04 | 5/30-6/11 | 7.5 | 6.5 | 1 | 0 - revising reat 2 - define the Security Design on the SDD document 3 - User actions registration and login and helper function to sanitize input 5 - participate in team meeting | 2 | 0 | 1 | 2 | 0.5 | 1 | 0

## Brenna Mahn
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/14 | 16 | 13.5 | 2.5 | 0 - Learn React 1 - define high level requirements 2 - Narrow down what we need to design for UI 3. Add bio to team.md 5 - make project plan, send reminders to team members, set up pivotal tracker, make tickets, familiarize team members with ticket format and task tracking expectations 6 - set up git 7 - research similar products, prepare presentation, fill in my sections of risk management form and SPPP | 3 | 3 | 2 |  |  | 2.5 | 1 | 2 | - Wrote 2 sections of SPPP - Wrote 3 sections of risk management form - Set up Pivotal Tracker and created tickets - Created personas - Documented requirements -Met with team 3 to determine their requirements | 1. Since our team is building UI for services being built by other teams, hard to define all our requirements without other teams having theirs settled yet. | Meeting with other teams to work out their plans for what services they are developing, fill in service gaps and resolve overlapping work. Once this is accomplished it should be clearer what UI my team needs to develop for the other team's services | 0 - Continue to watch tutorials and read React Documentation, consult team members who have React experience on what areas most important to focus on for our project 1 - Communicate with other teams on their UI needs and discuss with team how that translates into our requirements. | 12
2024-02-03 | 05/15-05/29 | 17 | 15 | 2 | 0 - Learn React 1 - Refine Requirements 2 - Create software design document and review wireframes 3.- Add project creation form feature 5 - make iteration plan, assigned tickets to team, communicated with other teams to define user and project classes and align requirements. 6 - set up react dependencies (node.js, npm, libraries) 7 - updated SPPP. risk management form, progress report, contributed to SDD, made slideshow and presentation video with help from Fehmi, compiled docs, made pre-release. | 4 | 1 | 2 | 2 |  | 1 | 1 | 4 | Made project form, coordinated work, did a few sections of SDD, made release | Getting the other teams' services so our UI can actually work with them. | Focused on building out main UI structure for now |  | 11
2024-03-04 | 5/30-6/11 | 16.5 | 14.5 | 2 | 0 - Learn React 1 - Prioritize requirements to translate into tasks and allocate resources 2 - Update software design document, review canva design 3.- Refactor project creation form to improve code, update styling to match canva design 4. Wrote test for my project form feature. Fixed test configuration after a PR caused them to stop running properly. Fixed teammate's test that was failing 5 - make iteration plan, assigned tickets to team, communicated with other teams to get updates on their services and how to begin integrating 6 - set up testing dependencies (adding jest, babel, configs) 7 - updated SDD. risk management form, progress report, compiled docs, made pre-release. | 1 | 0.5 | 1 | 4 | 2 | 2 | 1 | 3 | Updated form styling, wrote tests, communicated and coordinated team, made release | Did not get access to services until end of iteration, was difficult to know how to allocate resources without being able to work on most core functions which required the services. | While waiting for services pivoted the team to fleshing out design and doing any prep we could to integrate services without knowing full details yet. | Integration work to use the other teams services. Adding and executing testing Deployment | 12

## Savien Love
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/14 | 6.15 | 3.6 | 2.55 | 0 - learn about the project 1 - look at and estimate the requirements needed 2 - create pages for what we need to create, create basic react structure 5 - Make Zoom meetings 7 - prepare presentation | 1 | 0.5 | 1 | 0 | 0 | 0.1 | 0 | 1 | 1. Write design and implementation sections of SPPP- Risk Management 2. Write my intro for team.md 3. Create a page breakdown for what pages could be needed | 1. Confusion in the begining for overall requirements | 1. More communication for planning | 2- Wireframe 4 - Create React Basic Setup | 6
2024-02-03 | 05/15-05/29 | 3 | 1 | 2 | 2- Completed the outline for the React and Navigation, updated Figma Design 3 - Creating the Discussion, Search Bar, Cards, and information basic code 5 - Made Zoom Meeting 7- creating and uploading the demo video |  |  | 1.5 | 2 |  | 0.1 |  | 0.1 | 2. Completed the the outline fo react, Navigation, Dashbaord
2024-03-04 | 5/30-6/11 | 8.2 | 6.2 | 2 | 2- Updated SDD Document 3- Updating Project Card, Dashboard and adding in Project Modal and added in CSS for those pages 5- Talked with team and help with decisions. Updated meeting minutes. 7- Approved Github and reviewed code |  |  | 2 | 4 |  | 0.1 |  | 0.1 | 2- Updated SDD Document 3- Updating Project Card, Dashboard and adding in Project Modal and added in CSS for those pages 5- Talked with team and help with decisions. Updated meeting minutes. 7- Approved Github and reviewed code
4
5
6

## Fehmi Baltaci
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/14 | 6 | 4 | 2 | 0 - learn about the project 1 - look at and estimate the requirements needed 4 - Worked on the SPPP document for testing section. 1 - Worked on the Risk Management document for Requirements section. 4 - Worked on the Risk Management document for Testing section. 7 - Worked on the team.md and added the details for myself. 3 - Created a release for the iter0 from GitHub. | 1 | 1 |  | 0.5 | 1 |  | 0.5 |  | 1. Write design and implementation sections of SPPP- Risk Management 2. Write my intro for team.md 3.Write the section for QA Testing in SPPP doc. | Not having clear understaing about the application and its process. | Working on communicating with other teams on the requirements.
2024-02-03 | 05/15-05/29 | 8 | 6 | 2 | 4- Worked on the SPPP document for adding more details to the Testing section. 4 - Worked on the automation framework for testing using Python Behave and Selenium. The framework is not done, folder structure is somewhat done. 0 - Learn about the Behave-Selenium python framework. 7 - Worked on the slide for Testing section. 7 - Worked on the slide show video for the Testing section. 7 - Worked on the Progress Report. | 2 |  |  |  | 2 |  |  | 2 | - Worked on the Testing Framework for the application using Python Behave and Selenium. - Worked on the Testing section of SPPP and STD. | Don't have the UI yet for testing. | As a team we're working on the application and we'll have the UI in short time.
2024-03-04 | 5/30-6/11 | 13 | 11 | 2 | 7 - Worked on the Progress Report. 4- Worked on the STD document and added more details. 4 - Worked on the automation framework for testing using Python Behave and Selenium. The framework is not done, folder structure is somewhat done. 0 - Learn about the Behave-Selenium python framework. 3 - Worked on the Footer section for the application. | 2 |  |  | 3 | 4 |  |  | 2 | - Worked on the Testing Framework for the application using Python Behave and Selenium. - Worked on the Testing section of SPPP. - Worked on the STD document and updated it with more information. - Worked on the Footer component for the application. |  | We have the UI now ready and in progress of implemantation. I already added the test cases we're planing to automate and will automate them shortly this week.

## Pinwen Mu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/14 | 9.5 | 7 | 2.5 | 0 - learn about the project and Github 1 - define configuration management and technology competence 5 - Zoom meetings 6- set team's github repository and merge branches 7 - update readme file | 1 | 3.5 |  |  |  | 2.5 | 0.5 | 2 | 1. Write technologh competence of SPPP- Risk Management 2. Write my intro for team.md 3.Write the section for configuration management plan in SPPP doc. 4. write the readme file 5. set team's github repository and merge branches | not familar with pivotal tracker and github collaration process | basically solved by using these tools with teammates help | 0- learn react 3- start coding based on the design requirements 5- meeting and discussion around next steps | 12
2024-02-03 | 05/15-05/29 | 7 | 5 | 2 | 0- learn about the React 3- create landing page and navigation bar based on the design 5- Zoom meetings 6- manage github branches and merges | 1.5 |  |  | 3 |  | 2 | 0.5 |  | 1. Create the landing page 2. Create the navigation bar 3. Manage the GitHub branches and merges |  |  | 3- Refine the coding part and integrate it with the backend. 4- Test the features I developed 5- meeting and discussion around next steps
2024-03-04 | 5/30-6/11 | 15 | 13 | 2 | 3- Updating Landing page based on Canva. 3-Make navbar to be responsive and change states based on login/logout 3- set up the basic page style in index.css 4- retest the landing page with jest 5- Zoom meetings 6- manage github branches and merges 7- work on progress report and presentation |  |  |  | 9.5 | 1 | 2 | 0.5 | 2 | 3- Updating Landing page based on Canva. 3-Make navbar to be responsive and change states based on login/logout 3- set up the basic page style in index.css 4- retest the landing page with jest 5- Zoom meetings 6- manage github branches and merges 7- work on progress report and presentation | I used mocha for the testing part in lab3 and has some conflicts with jest