## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members |  | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more team members get added to the team | 1 | 2 | 2 | 40 | team leader and all members |  | Redefine the project scope if necessary, and adjust team assignments to include new members. | No one has been added to the team so far | Open
| Lack of motivation or responsibility | Team members may become unmotivated or fail to take responsibility for their tasks, leading to delays or subpar work quality. | 3 | 4 | 3 | 18 | team leader and all members |  | Have regular checkins with feedback, recognitions for achievements, and offer support. Make responsibilities clear and tasks achievable. | So far team has been motivated and engaged | Open
Communication | duplicate work | Lack of communication causes team members to work on the same task, resulting in wasted time and resources. | 2 | 4 | 3 | 24 | team leader and all members |  | Use task management tool to ensure tasks are clearly assigned and progress can be tracked. Provide frequent updates on task progress. | Communication has been sufficient to prevent this issue so far | Open
| worked on wrong components | Misunderstandings result in team members working on the wrong components of the project. | 2 | 4 | 3 | 24 | team leader and all members |  | Maintain clear requirements documentation and communicate often and assess that work aligns with requirements | Communication has been sufficient to prevent this issue so far | Open
| useless work | Lack of clear communication or understanding of project goals and requirements may lead to team members spending time on tasks that are ultimately unnecessary. | 2 | 4 | 3 | 24 | team leader and all members |  | Ensure that project goals and requirements are clearly communicated and understood by all team members. Regularly review and prioritize tasks to focus efforts on high-value activities. | Communication has been sufficient to prevent this issue so far | Open
| inconsistent work | Lack of standardized processes or communication leads to inconsistent quality or approaches in completing tasks. | 3 | 3 | 3 | 27 | team leader and all members |  | Establish clear guidelines, standards, and best practices for task execution and deliverable quality. Encourage regular peer reviews and feedback sessions to identify and address inconsistencies. | Communication has been sufficient to prevent this issue so far | Open
Requirements | unclear requirements | Requirements for the application is not clear, leading to an application with features that's not meant to be/not be there | 2 | 3 | 2 | 24 | team leader and all members | 2024-06-01 | Talk to other teams and within the team, keep getting the latest requirements. | Have regular meetings with other teams and within the team. | Open
| scope creep | Requirements expanded and impelentation couldn't catch the requiremtns causing development process to fail. | 2 | 2 | 2 | 32 | team leader and all members | 2024-06-01 | Define the requirements in the beginning of the projects and stick to the plan. | Keep an eye on the project scope and have regular checks. | Open
| constant requirements changes | Constant requirement change will cause wasting time on refactoring/changing the features. | 3 | 3 | 3 | 27 | team leader and all members | 2024-06-01 | Not be too much flexiable for the requirements. | Have a requirements sheet for the application. | Open
| Overly complex requirements | Requirements that are too complex will hard to be implemented. | 2 | 1 | 3 | 60 | team leader and all members | 2024-06-01 | Don't get too complex requirements. | This should be made clear with other teams as well. | Open
| Unrealistic customer expactations | Unrealistic scenario expextations from the application, like too many features, user types etc. | 3 | 1 | 2 | 30 | team leader and all members | 2024-06-01 | Requirements should made clear by the user and team has to be in contact with the customer for not going too unrealistic req. | Have limits. | Open
| Too many requirement | A lot of requirement will cause issues while implementing the application. | 2 | 2 | 4 | 64 | team leader and all members | 2024-06-01 | Plan to build the application. | Have limits. | Open
| Cross-functional Misalignments | Miscommunication on the feature with other teams. | 4 | 3 | 3 | 18 | team leader and all members | 2024-06-01 | Get all teams contact with each other throughout the application build. | Be in touch with other teams | Open
| Lack of Prioritization of Requirements | Having no clear priority for the requirement | 4 | 2 | 2 | 16 | team leader and all members | 2024-06-01 | Have priority for each req. | Plan for each req. | Open
| Documantation Gaps | Lack of not documenting the requirements. | 2 | 3 | 1 | 12 | team leader and all members | 2024-06-01 | Someone should be in charge of documantation and review. | Document constantly. | Open
Management | improper task assignments | Tasks are assigned to team members without considering their skills, expertise, or workload, leading to inefficiencies and potential delays. | 3 | 4 | 3 | 18 | team leader | 2024-06-01 | Conduct a thorough assessment of team members' skills, expertise, and workload before assigning tasks. Match tasks to individuals based on this. Regularly review task assignments and adjust as needed. | Team meetings have been conducted to assess proper task assignments | Open
| improper planning | Inadequate or incomplete project planning leads to uncertainties, delays, or failure to meet objectives. | 4 | 5 | 4 | 8 | team leader | 2024-06-01 | Invest sufficient time and resources upfront to conduct project planning, including defining clear objectives, scope, deliverables, timelines, and resource requirements. Regularly review and update the project plan as needed. | Planning has been started and is progressing well so far | Open
| lack of management skills | Insufficient or inexperienced management leads to ineffective decision-making, poor team coordination, and inadequate project oversight. | 3 | 4 | 4 | 24 | team leader | 2024-06-01 | Encourage open feedback and communication channels to identify and address any gaps or challenges in management skills proactively. | Team lead is working on getting to know team members to determine most fitting management strategy | Open
Technology competence | Not familiar with the framework used | Lack of experience with the React, potentially slowing progress and affecting quality. | 3 | 4 | 5 | 30 | All team member | 2024-06-01 | Team member search for React courses and resources. Design Leader helps other members with technical difficulties. | Team members are getting familiar with React | Open
| Not familiar with the programming language used | inexperienced with JavaScript, which could lead to inefficiencies and errors in code. | 2 | 3 | 3 | 36 | All team member | 2024-06-01 | Team member search for JavaScript courses and resources. Design Leader helps other members with technical difficulties. | Team members are getting familiar with JavaScript | Open
| Not familiar with unit testing | Lack of knowledge in creating and executing unit tests, which are essential for verifying the functionality of individual parts of the software. | 3 | 3 | 3 | 27 | All team member | 2024-06-01 | Learn test skills from this class. QA Leader will help others with test question | Team members are getting familiar with test | Open
| Not familiar with AWS | Lack of experience with the AWS, potentially causing deployment failure. | 5 | 5 | 5 | 5 | All team member | 2024-06-01 | Team member will work together and learn how to deploy on AWS by online tutorial. Ask facilitator for help when we are stuck | Later after React learning and implementation | Open
| Not familiar with Git | Team members have limited experience using Git for version control, which is crucial for managing changes to the project codebase effectively. | 1 | 1 | 1 | 25 | All team member | 2024-06-01 | we can ask for help on discord | keep communicate with teammates | Open
Design and implementation | Improper design | Design is not befitting of the project we are creating | 2 | 4 | 4 | 32 | Design Leader and all memeber | 2024-06-01 | Come into it with properly detailed and reliable design fully thought out | Create wireframe and distribute between members for full acess | Open
| improper technology stack | The technology pack does not meet the requirements for the project | 2 | 4 | 4 | 32 | Design Leader and all team members | 2024-06-01 | Research tech stack needed and what would work and look best with code | Research technology used during wireframe process | Open
| Messy code | Code that does not follow best practices for everyone to understand | 2 | 3 | 4 | 48 | All team member | 2024-06-01 | Discuss how we will be submitting and writing code before we actually code | Create a detailed discussion about how code will be handled | Open
Testing | Not enough testing | Not enough testing for the applications all components and functions. | 3 | 2 | 4 | 48 | All team member | 2024-06-01 | The automation process will begin immediately. Then we'll plan to have enough testing for the whole system | Create an automation for the application right after the first deployment. | Open
| Depending on external systems | In our case, we're depending on other teams on most of the things. We cannot build an automated test for those functions. | 3 | 2 | 4 | 48 | All team member | 2024-06-01 | We'll be in communication with other teams the whole time. | Communicate with other teams for the test cases that we'e depending on. | Open
| Not having a stable environment | Our application will get updated almost everyday. In that case, it's impossible to have an automated tests. | 3 | 2 | 3 | 36 | All team member | 2024-06-01 |  |  | Open
| Not having Performance Testing | Not having performance testing for our application will cause problems when there is a load on the systems. | 3 | 2 | 2 | 24 | All team member | 2024-06-01 |  |  | Open
| Not enough data for testing | We'll have different users in the system and if we don't have those users types for testing in hand, then we won't be able test those functions. | 3 | 2 | 3 | 36 | All team member | 2024-06-01 | We'll contact to other teams to create dummy data for us. | Dummy data will be used for the testings. | Open
| Not having security testing | Not having security testing will cause security issues for the application. | 3 | 2 | 2 | 24 | All team member | 2024-06-01 |  |  | Open
| Having only manual testing | Because we're building this application in such a short time and the systems are not stable, we might have to skip automating some of the functions in the application. And this will cause insufficient testing. | 3 | 2 | 5 | 60 | All team member | 2024-06-01 | Automation will start along with manual testing. | We'll work on the automation while we're building the application. | Open
Integration and deployment | Not enough time for integration and deployment | Insufficient time allocated for integrating various components and deploying the software, leading to rushed or incomplete deployment, potential errors, and operational issues. | 2 | 2 | 1 | 16 | All team member | 2024-06-18 | Allocate sufficient time in the project schedule specifically for integration and deployment activities |  | Open
| Integration Complexity | Integrating multiple microservice and ensuring they work seamlessly with frontend components | 4 | 2 | 1 | 8 | All team member | 2024-06-18 | Start working and communicatiing with other team performing microservice as soon as possible and work on conitnuous integration |  | Open
| Deployment Failure | Potential issue in deploying updates or adding new features leading to service desruption. | 2 | 1 | 2 | 40 | All team member | 2024-06-18 | Keep log of the failure and work to resolve the issue. |  | Open
| Security Vulnerability | Introduction of security flaws during integration or deployment that could be exploited. | 1 | 2 | 3 | 60 | Security Lead | 2024-06-18 | Access as much as security vulnerabilities the system could face before deployment and take security measures |  | Open
| Service Downtime | The risk of unexpected downtime during deployment, affecting user access and system reliability. | 1 | 3 | 2 | 30 | All team member | 2024-06-18 | Debug and refactor implemetation to resolve the downtime of the service |  | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.