## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/10-05/14 | Team structure: Collaboratively assigned team roles, established weekly meetings and communication expectations. Planning: Team lead documented requirements with assistance from other team members, each member contributed to filling out SPPP and risk management form, Technical setup: Team lead set up pivotal tracker, configuration lead created github repo and team members joined and added their bios. Team lead reviewed changes and config lead merged into main branch, Presentation: Brooke took the lead on distilling iteration 0 work into presentation slideshow and video | Not all members familiar with Pivotal Tracker and had to get up to speed on how it works. Technical progress is waiting on product requirement clarity before implementation. Not all team members have React experience so this is expected to add some challenges as we move forward. | Requirements were difficult to determine as we are reliant on the other team's decisions to determine what they need. | Preliminary requirements were documented but continuing to communicate across teams to refine their accuracy to all teams' needs. | 18 | 2 |  |  |  | 43.5 | Brenna - 16 Brooke - 6 Natanim - 8 Lillian - 9.5 Fehmi - 6 | 2.5
1 | 05/15-05/29 | Solidifying requirements: Meeting with all teams and professor allowed us to get a clearer idea of our requirements and which teams we'll be working with for our backend. We made the decision not to support team 3's learning platform to narrow our scope. Cross team collaboration: Team lead communicated with other teams and reviewed their documents to understand their services and make sure our UI will align with them on pieces like login type, and project fields. Project structure: Brooke, our design and Implementation lead created a skeleton React project to get us started and determined a file organization strategy in collaboration with our team. Beginning development: Brooke began development, creating a 404 error page and building out our navigation, and beginning to build our dashboard UI. All other team members have also been assigned tickets and are focusing on building out UI for our most important features this iteration. Integration with backend will be a focus next iteration when other teams have had more time to setup their services. Configuration lead has been merging PRs whenever they are ready. | There were some difficulties getting everyone's local projects in sync and there was some confusion around pull requests. We worked on getting our project files organized the same and only pushing the necessary files to reduce merge conflicts and getting team familiar with the PR process. | Requirements changed at the beginning of this iteration which meant we needed to rework some of our plans. The exact details of how we will integrate our UI with other teams' services is still to be determined and remains a challenge for us. Additionally, two team members had to take trips out of town, impairing development tool access and slowing progress. | Requirements have now been determine so solid progress was made there. Will need to continue cross team communication for integration moving forward. | 18 | 4 |  |  |  | 47 | Brenna - 17 Brooke - 3 Natanim - 12.5 Lillian - 8 Fehmi - 7 | 2 | 9.5 | 1 | 6 | 8 | 2.5 | 3.6 | 1.5
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Brenna Mahn
Savien Brooke Love
Fehmi Baltaci
Natanim Eibrahim
Pinwen Mu

## Natanim Eibrahim
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/08-05/16 | 8 | 5.5 | 2.5 | 0 - learn pivotal tracker and watch tutorials 1 - define non-functonal requirements 5 - participate in team meetings 6 - revise and setup git 7 - work on the project overview 7 - research similar projects and similar products and work on the related work of the the SPPP document 7 - define the mangement plan of the SPPP document 7 - work on the Integration and deployment risk management details 7 - work on lab1 and collaborate with team | 1.5 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1. Participated in 4 section of the SPPP document 2. Write 1 section (Integration and Deployment) if the Risk Management 3. Setup git and collaborate on lab1 team.md update my information and created a commit message | 1. not familar with pivotal tracker 2. |  | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 05/18-05/23 | 8.5 | 7.5 | 1 | 0 - revising react and pivotal tracker 3 - Registration and Login Form 5 - Participate in team meetings 7 - work on lab 2 7 - create user story tickets on pivotal tracker | 3 | 0 | 1.5 | 1 | 0.5 | 0.5 | 0 | 1
3 | 05/23-05/28 | 4 | 3 | 1 | 0 - revising reat 2 - define the Security Design on the SDD document 3 - User actions registration and login and helper function to sanitize input 5 - participate in team meeting | 2 | 0 | 1

## Brenna Mahn
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/7-05/14 | 16 | 13.5 | 2.5 | 0 - Learn React 1 - define high level requirements 2 - Narrow down what we need to design for UI 3. Add bio to team.md 5 - make project plan, send reminders to team members, set up pivotal tracker, make tickets, familiarize team members with ticket format and task tracking expectations 6 - set up git 7 - research similar products, prepare presentation, fill in my sections of risk management form and SPPP | 3 | 3 | 2 |  |  | 2.5 | 1 | 2 | - Wrote 2 sections of SPPP - Wrote 3 sections of risk management form - Set up Pivotal Tracker and created tickets - Created personas - Documented requirements -Met with team 3 to determine their requirements | 1. Since our team is building UI for services being built by other teams, hard to define all our requirements without other teams having theirs settled yet. | Meeting with other teams to work out their plans for what services they are developing, fill in service gaps and resolve overlapping work. Once this is accomplished it should be clearer what UI my team needs to develop for the other team's services | 0 - Continue to watch tutorials and read React Documentation, consult team members who have React experience on what areas most important to focus on for our project 1 - Communicate with other teams on their UI needs and discuss with team how that translates into our requirements. | 12
2 | 5/15-5/29 | 17 | 15 | 2 | 0 - Learn React 1 - Refine Requirements 2 - Create software design document and review wireframes 3.- Add project creation form feature 5 - make iteration plan, assigned tickets to team, communicated with other teams to define user and project classes and align requirements. 6 - set up react dependencies (node.js, npm, libraries) 7 - updated SPPP. risk management form, progress report, contributed to SDD, made slideshow and presentation video with help from Fehmi, compiled docs, made pre-release. | 4 | 1 | 2 | 2 |  | 1 | 1 | 4

## Savien Love
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 6.15 | 3.6 | 2.55 | 0 - learn about the project 1 - look at and estimate the requirements needed 2 - create pages for what we need to create, create basic react structure 5 - Make Zoom meetings 7 - prepare presentation | 1 | 0.5 | 1 | 0 | 0 | 0.1 | 0 | 1 | 1. Write design and implementation sections of SPPP- Risk Management 2. Write my intro for team.md 3. Create a page breakdown for what pages could be needed | 1. Confusion in the begining for overall requirements | 1. More communication for planning | 2- Wireframe 4 - Create React Basic Setup | 6
2 | 05/18-05/28 | 3 | 1 | 2 | 2- Completed the outline for the React and Navigation, updated Figma Design 3 - Creating the Discussion, Search Bar, Cards, and information basic code 5 - Made Zoom Meeting 7- creating and uploading the demo video |  |  | 1.5 | 2 |  | 0.1 |  | 0.1 | 2. Completed the the outline fo react, Navigation, Dashbaord

## Fehmi Baltaci
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 6 | 4 | 2 | 0 - learn about the project 1 - look at and estimate the requirements needed 4 - Worked on the SPPP document for testing section. 1 - Worked on the Risk Management document for Requirements section. 4 - Worked on the Risk Management document for Testing section. 7 - Worked on the team.md and added the details for myself. 3 - Created a release for the iter0 from GitHub. | 1 | 1 |  | 0.5 | 1 |  | 0.5 |  | 1. Write design and implementation sections of SPPP- Risk Management 2. Write my intro for team.md 3.Write the section for QA Testing in SPPP doc. | Not having clear understaing about the application and its process. | Working on communicating with other teams on the requirements.
2 | 05/18-05/28 | 8 | 6 | 2 | 4- Worked on the SPPP document for adding more details to the Testing section. 4 - Worked on the automation framework for testing using Python Behave and Selenium. The framework is not done, folder structure is somewhat done. 0 - Learn about the Behave-Selenium python framework. 7 - Worked on the slide for Testing section. 7 - Worked on the slide show video for the Testing section. 7 - Worked on the Progress Report. | 2 |  |  |  | 2 |  |  | 2 | - Worked on the Testing Framework for the application using Python Behave and Selenium. - Worked on the Testing section of SPPP and STD. | Don't have the UI yet for testing. | As a team we're working on the application and we'll have the UI in short time.

## Pinwen Mu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9.5 | 7 | 2.5 | 0 - learn about the project and Github 1 - define configuration management and technology competence 5 - Zoom meetings 6- set team's github repository and merge branches 7 - update readme file | 1 | 3.5 |  |  |  | 2.5 | 0.5 | 2 | 1. Write technologh competence of SPPP- Risk Management 2. Write my intro for team.md 3.Write the section for configuration management plan in SPPP doc. 4. write the readme file 5. set team's github repository and merge branches | not familar with pivotal tracker and github collaration process | basically solved by using these tools with teammates help | 0- learn react 3- start coding based on the design requirements 5- meeting and discussion around next steps | 12
2 | 05/18-05/28 | 7 | 5 | 2 | 0- learn about the React 3- create landing page and navigation bar based on the design 5- Zoom meetings 6- manage github branches and merges | 1.5 |  |  | 3 |  | 2 | 0.5 |  | 1. Create the landing page 2. Create the navigation bar 3. Manage the GitHub branches and merges |  |  | 3- Refine the coding part and integrate it with the backend. 4- Test the features I developed 5- meeting and discussion around next steps